## Project tasks
Name | Priority | Assigned to
WEDDING PLAN | Medium
Agree budget and approach | Important | Deb Ashby, Ben Lee
Set wedding date | Urgent | Deb Ashby, Ben Lee
PREPARATION | Medium
ATTIRE | Medium
Select and order wedding dress | Important
Select wedding dress | Medium | Deb Ashby
Order dress | Medium | Deb Ashby
Measurements and fitting | Medium | Deb Ashby
Select and order bridesmaids dresses | Important | Deb Ashby
Select and order groom tuxedo | Important | Ben Lee
Select and order best man tuxedo | Important | Ben Lee, Jack Wilkinson
GUESTS | Medium
Make guest list | Medium | Deb Ashby, Ben Lee
Send out invitations | Medium | Deb Ashby
Finalize guest list | Medium | Ben Lee, Deb Ashby
Book guest accommodation | Medium | Olivia Hyde
RECEPTION VENUE | Medium
Make reception venue short list | Medium | Ben Lee, Deb Ashby, Olivia Hyde, Jack Wilkinson
Book reception venue | Important | Ben Lee, Deb Ashby
Plan and finalize seating arrangements | Medium | Deb Ashby, Ben Lee
CATERING | Medium
Make caterer short list | Medium | Deb Ashby, Ben Lee
Book caterer and finalize menu | Medium | Deb Ashby, Ben Lee
Make baker short list | Medium | Deb Ashby
Select baker and order cake | Medium | Deb Ashby
FLOWERS | Medium
Make florist short list | Medium | Deb Ashby
Select florist and order flowers | Medium | Deb Ashby
MEMORIES | Medium
Make photographer short list | Medium | Deb Ashby, Ben Lee
Select and book photographer | Medium | Ben Lee
DETAILS | Medium
Select and buy rings | Medium | Deb Ashby, Ben Lee
Select and book entertainment | Medium | Jack Wilkinson, Olivia Hyde
Select and book transport | Medium | Jack Wilkinson
Register wedding and get license | Medium | Deb Ashby, Ben Lee
WEDDING VENUE | Medium
Make wedding venue short list | Medium | Deb Ashby, Ben Lee
Book wedding venue | Medium | Ben Lee
HONEYMOON | Medium
Make honeymoon destination short list | Medium | Deb Ashby, Ben Lee
Select honeymoon destination and book | Medium | Deb Ashby, Ben Lee
Rehearsal | Important | Andrea Nowak, Olivia Hyde, Jack Wilkinson, Deb Ashby, Ben Lee
Wedding day | Important | Andrea Nowak, Olivia Hyde, Jack Wilkinson, Deb Ashby, Ben Lee