## Sheet1
Project Title: Campaign Management
Bucket | Task Name | Progress | Priority | Start Date | Due Date | Assigned to | Attachments | File | Labels
Planning | Collect campaign information | Complete | Medium | 2022-10-02 | 2022-10-09 | You | Y | Campaign_Info.docx | Phase 1
| Finalise campaign brief | Complete | Medium | 2022-10-10 | 2022-10-17 | You | Y | Campaign_Brief.docx | Phase 1
| Kickoff meeting | Complete | Important | 2022-10-14 | 2022-10-21 | You | N |  | Phase 1
| Creative brainstorm | Complete | Low | 2022-10-15 | 2022-10-22 | You | N |  | Phase 1
Content Development | Develop messaging framework | In Progress | Medium | 2022-10-20 | 2022-10-27 | You | Y | Message_Framework.pdf | Phase 2
| Create marketing materials | In Progress | Medium | 2022-10-25 | 2022-11-01 | You | N |  | Phase 2
| Create templates | Not Started | Medium | 2022-10-25 | 2022-11-01 | You | N |  | Phase 2
| New asset designs | Not Started | Medium | 2022-10-25 | 2022-11-01 | You | N |  | Phase 2
| Collate quotes and custom feedback | Not Started | Low | 2022-10-26 | 2022-11-02 | You | Y | Quotes.docx | Phase 3
Campaign Promotion | Draft social media promotion plan | Not Started | Important | 2022-11-01 | 2022-11-08 | You | N |  | Phase 3
| Create campaign emails | Not Started | Medium | 2022-11-02 | 2022-11-09 | You | N |  | Phase 3
| Develop sales outreach plan | Not Started | Important | 2022-11-04 | 2022-11-11 | You | N |  | Phase 3