## Sheet1
Project Title: Product Launch | [9 empty] | Legend:
[10 empty] | Bold font | Top-level Summary Tasks
Task ID | Task Name | Start Date | Finish Date | Completion | Bucket | Priority | Dependencies | Note | Team | Red font | Second-level Summary Tasks
1 | Q1 | [8 empty] | Blue font | Subtasks
2 | Preparation
3 | New mobile app | 2022-11-02 | 2022-11-16 | 100% | Prep | Important |  |  | Development
4 | New user on-boarding updates | 2022-11-17 | 2022-11-22 | 100% | Prep | Important |  |  | Development
5 | Product training | 2022-11-24 | 2022-12-08 | 75% | Prep | Important | 3,4 | Fully brief training team | Training
6 | Q2
7 | Updates and Testing
8 | App performance improvements | 2022-12-12 | 2022-12-19 | 50% | Testing | Urgent |  |  | Product
9 | Offline mode | 2022-12-19 | 2022-12-27 | 20% | Testing | Urgent |  |  | Product
10 | User testing | 2023-01-02 | 2023-01-16 | 10% | Testing | Medium | 8,9 | Establish test group | Product
11 | New integration | 2023-01-17 | 2023-01-23 | 0% | Testing | Medium |  |  | Development
12 | Test notifications | 2023-01-22 | 2023-01-24 | 0% | Testing | Medium |  |  | Development
13 | Q3
14 | Analysis
15 | Reporting and analytics updates | 2023-01-20 | 2023-01-25 | 0% | Analysis | Medium |  |  | Development
16 | App design refresh | 2023-01-27 | 2023-01-30 | 0% | Analysis | Medium | 10 |  | Development
17 | New search functionality | 2023-02-02 | 2023-02-09 | 0% | Analysis | Important | 10,16 |  | Development
18 | Sign off | 2023-02-09 | 2023-02-09 | 0% | Analysis | Important |  | Get sign off from management | Product
19 | Q4
20 | Rollout
21 | Deploy to test group | 2023-02-15 | 2023-02-17 | 0% | Deployment | Medium | 18 |  | Product
22 | Collate test group results | 2023-02-20 | 2023-02-27 | 0% | Deployment | Medium | 21 |  | Product
23 | Review and update | 2023-03-01 | 2023-03-13 | 0% | Deployment | Medium | 18,21 |  | Development
24 | Deploy to users | 2023-03-20 | 2023-03-24 | 0% | Deployment | Medium | 23 |  | Product
25 | Documentation | 2023-03-20 | 2023-03-30 | 25% | Deployment | Low |  |  | Training
Formulas:
Finish Date = [Start Date]+14